## Budget & Time Investment
2CODE — MONTHLY MARKETING PLAN ($100/mo + Your Time)
Total Cash: $100/month · Total Time: ~10-12 hrs/week · 6-Month Cash Spend: $600
Channel | Monthly Cost | Hours/Week | Weekly Tasks | Monthly Output | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | 6-Month Total
Google Ads (Paid) | 100 | 1-2 hrs | Monitor CPC, adjust bids, test ad copy, add negative keywords | 35-100 clicks, 1-3 leads | 100 | 100 | 100 | 100 | 100 | 100 | 600
Upwork + Mostaql | 0 | 4-5 hrs | Browse jobs daily, write 10-15 proposals/week, follow up on responses | 40-60 proposals, 1-2 clients | 0 | 0 | 0 | 0 | 0 | 0 | 0
LinkedIn Organic | 0 | 2-3 hrs | Write 2-3 posts/week (project showcases, tips), engage with prospects, connect with decision-makers | 10-12 posts, 20+ new connections | 0 | 0 | 0 | 0 | 0 | 0 | 0
Google Business Profile | 0 | 0.5 hrs | Respond to reviews, post updates, add photos of work | 2-4 posts, updated portfolio | 0 | 0 | 0 | 0 | 0 | 0 | 0
Directories (Clutch/GoodFirms) | 0 | 0.5 hrs | Update portfolio, request client reviews, respond to inquiries | 1-2 new reviews requested | 0 | 0 | 0 | 0 | 0 | 0 | 0
SEO (Organic from website) | 0 | 1-2 hrs | Monitor Search Console, check rankings, tweak meta tags if needed | Track keyword positions, fix issues | 0 | 0 | 0 | 0 | 0 | 0 | 0
TOTAL | 100 | 10-12 hrs |  |  | 100 | 100 | 100 | 100 | 100 | 100 | 600
Note: $0 channels are FREE but require consistent time investment. The hours/week column shows your real commitment.

## Revenue Projections
2CODE — 6-MONTH REVENUE PROJECTIONS
KEY ASSUMPTIONS
Average deal size (landing page) | 2500 | Based on your $1,500-$5,000 range
Average deal size (e-commerce) | 10000 | Based on your $5,000-$15,000 range
Average deal size (blended) | 3500 | Weighted toward smaller early projects
Google Ads CPC (Egypt) | 2 | Average for web dev keywords
Google Ads monthly clicks | 50 | At $100 budget / $2 avg CPC
Google Ads conversion rate | 3% | 3% of clicks become leads
Upwork win rate | 5% | 5% of proposals win (conservative)
Total marketing spend (6 months) | 600 | Cash only, not counting time
MONTHLY REVENUE BY SOURCE
Month | Google Ads | Upwork/Mostaql | LinkedIn/Referral | Other (Directories, Organic) | TOTAL Revenue | Cumulative
Month 1 | 0 | 1500 | 0 | 0 | 1500 | 1500
Month 2 | 0 | 2000 | 0 | 0 | 2000 | 3500
Month 3 | 2500 | 2000 | 0 | 0 | 4500 | 8000
Month 4 | 2500 | 3500 | 1500 | 0 | 7500 | 15500
Month 5 | 3500 | 3500 | 2500 | 1000 | 10500 | 26000
Month 6 | 3500 | 5000 | 3500 | 1500 | 13500 | 39500
6-MONTH TOTAL | 12000 | 17500 | 7500 | 2500 | 39500 | 39500
Total Marketing Spend (Cash) | 600
Total Revenue | 39500
ROI | 64.8333
Estimated Clients (6 months) | 5-10

## Channel Strategy
2CODE — CHANNEL STRATEGY & EXPECTED METRICS
Channel | Monthly Cost | Time/Week | What You Do | Expected Leads/Mo | Close Rate | Clients/Mo | Avg Deal | Revenue/Mo
Google Ads | 100 | 1-2 hrs | Run search ads for "web development Egypt", "landing page Cairo", "تصميم مواقع مصر". Monitor & optimize weekly. | 1-3 | 25% | 0.5-1 | 3000 | $1,500-$3,000
Upwork + Mostaql | 0 | 4-5 hrs | Apply to 10-15 relevant jobs/week. Write custom proposals. Build 5-star reviews. Raise rates over time. | 8-16 responses/mo | 10-15% | 1-2 | 2000 | $2,000-$4,000
LinkedIn Organic | 0 | 2-3 hrs | Post project showcases, web dev tips, case studies 2-3x/week. Connect with startup founders & marketing managers in KSA/UAE. | 1-2 | 20% | 0-0.5 | 5000 | $0-$2,500
Google Business Profile | 0 | 30 min | Keep profile updated with projects, respond to reviews, post monthly updates. Appears in "web agency near me" searches. | 0-1 | 30% | 0-0.3 | 3000 | $0-$1,000
Directories | 0 | 30 min | Maintain Clutch, GoodFirms profiles. Request reviews from every completed project. Update portfolio quarterly. | 0-1 | 20% | 0-0.2 | 4000 | $0-$800
SEO / Organic | 0 | 1-2 hrs | The SEO work we already did on your site. Monitor Search Console, track rankings, iterate on content. Compounds over time. | 0-1 (grows) | 15% | 0-0.2 | 3500 | $0-$700 (growing)
KEY INSIGHT: Upwork is your #1 client source in months 1-3. Google Ads takes 2-3 months to optimize. LinkedIn and SEO are long-term plays that compound.

## 6-Month Timeline
2CODE — 6-MONTH ACTION TIMELINE
When | Channel | Action Items | Expected Result | Cost | Time Needed
Week 1 | Setup | Create Google Business Profile (add address, photos, services) Create Upwork profile (portfolio, rates, bio) Create Mostaql profile Set up Google Ads account + billing | All accounts live and ready | $0 | 6-8 hours
Week 2 | Launch | Launch Google Ads: 3-5 keywords in English + Arabic Submit first 10 Upwork proposals Publish first 2 LinkedIn posts (project showcase) | First clicks, first proposals sent | $25 | 10-12 hours
Week 3 | Execute | Send 10-15 more Upwork proposals Check Google Ads: pause bad keywords, lower bids on expensive ones Post 2-3 LinkedIn updates Respond to any leads | First Upwork responses, ad data | $25 | 10-12 hours
Week 4 | Optimize | Review Google Ads CTR & CPC data Add Arabic keyword campaign Add negative keywords Follow up on all Upwork conversations Request Google Business review from past client | First month data, pipeline forming | $50 | 8-10 hours
Month 2 | Build | Continue 10-15 Upwork proposals/week Optimize Google Ads (should have enough data) Create Clutch profile Post 2-3x/week on LinkedIn Land first 1-2 Upwork projects | First revenue, first reviews coming | $100 | 10-12 hrs/week
Month 3 | Convert | Google Ads leads should start converting Complete first projects, request reviews Portfolio growing — update all profiles Start engaging KSA/UAE prospects on LinkedIn | 2-3 active projects, 1-2 reviews | $100 | 10-12 hrs/week
Month 4 | Scale | Double down on winning Google Ads keywords Raise Upwork rates slightly (you have reviews now) Ask happy clients for referrals LinkedIn network growing | 3-4 total clients, referral pipeline | $100 | 8-10 hrs/week
Month 5 | Compound | Referrals should start coming in Upwork profile has momentum (reviews, ratings) SEO traffic growing from website changes Consider increasing Google Ads to $150-200 if ROI is good | 4-6 total clients, inbound growing | $100 | 8-10 hrs/week
Month 6 | Review & Plan | Full performance review across all channels Calculate actual ROI per channel Decide: increase budget? Drop weak channels? Plan Phase 2 strategy based on real data | 5-10 total clients, clear next steps | $100 | 6-8 hrs/week
TOTAL |  |  |  | $600 | ~10-12 hrs/week avg